## 89199 1
Project | Tracker | Parent task | Parent task subject | Status | Priority | Subject | Description | Author | Start date | Estimated time | Sprint | Private
2024 Summer Intern | Tasks | #89199 | [AIOps] Confirm architecture of linking LLM API & customized plugin | New | Normal | [5 empty] | 2024 Intern S1 | No
[6 empty] | discuss with michael | 確認 chat api 能否支援我們的需求 |  |  | 0.5
[6 empty] | architecture design | 系統架構圖/流程圖/資料庫設計圖 |  |  | 3
[6 empty] | discuss with PO |  |  |  | 2
[6 empty] | revise after discussion |  |  |  | 1.5
[6 empty] | lock down with PO |  |  |  | 1
[6 empty] | redis(mapping user and chat_id) |  |  |  | 4
[6 empty] | research teams webhook | include how to get chat id, user id and give user a select field to decide create new chat or use old chat |  |  | 3
[6 empty] | research line webhook | include how to get chat id, user id and give user a select field to decide create new chat or use old chat |  |  | 3
[6 empty] | define webhook interface |  |  |  | 1
[6 empty] | implement teams webhook |  |  |  | 4
[6 empty] | implement line webhook |  |  |  | 4
[6 empty] | dockerize webhook service |  |  |  | 1
[6 empty] | research prometheus api and PromQL |  |  |  | 3
[6 empty] | get metrics from prometheus api |  |  |  | 3
[6 empty] | integrate and format metrics |  |  |  | 3
[6 empty] | fine tune assistant prompt |  |  |  | 4
[6 empty] | dockerize chat assistant |  |  |  | 1
[6 empty] | AIOps API design |  |  |  | 2
[6 empty] | AIOps API review |  |  |  | 2
[6 empty] | define repository / usecase interface |  |  |  | 1
[6 empty] | design logger |  |  |  | 4
[6 empty] | use chat api (repository) |  |  |  | 4
[6 empty] | chat function (usecase) | create new chat / chat |  |  | 4
[6 empty] | write api (handler) | create new chat / chat |  |  | 4
[6 empty] | dockerize api | create new chat / chat |  |  | 1
[9 empty] | Total： | 64